## Sheet1
Date | Meeting Type | Outcome | Members
2022-01-26 | Sprint Planning | Created Initial User Stories, DoD, and selected stories. | Zach, Howard, Imran, Ikenna
2022-01-28 | Stand up | After feedback, renamed user stories to align with scrum. | Zach, Howard, Imran, Ikenna
2022-02-02 | Stand up | Discussed progress on User Stories. Decided on Django framework. | Zach, Howard
2022-02-09 | Stand up | Peer Reviewed with no issues. Video Upload, Django framework, and templates complete and finished sprint | Zach, Howard, Imran, Ikenna, Robbie
2022-02-09 | Client Meeting | Happy with initial Creation. Asked to emphasize Key Element Selection and Data Extraction Next Sprint. | Zach, Howard, Imran, Ikenna, Robbie
2022-02-09 | Sprint Review | Discussed how things went and what we could do to improve. Communication and better understanding of what everyone is working on. | Zach, Howard, Imran, Ikenna, Robbie
2022-02-10 | Sprint Planning | Refined Backlog and selected stories for next sprint. User login, Video Selection, Tensorflow | Zach, Howard, Imran
2022-02-16 | Stand up | Data extraction is proving difficult and will probably not be finished by the end of the sprint. Finished Video selection. | Zach, Howard, Imran
2022-02-23 | Stand up | Finished integrating login and video selection with overall project. Data extraction not completed and will move to sprint 3 | Zach, Howard, Imran, Ikenna, Robbie
2022-02-23 | Client Meeting | Discussed challenges with data extraction. Next sprint has emphasis on Dashboard presentation and data extraction. | Zach, Howard, Imran, Ikenna, Robbie
2022-02-23 | Sprint Review | We discussed how we need multiple people working on data extraction. | Zach, Howard, Imran, Ikenna, Robbie
2022-03-02 | Sprint Planning | Refined Backlog and selected stories for next sprint. Discussed need to be committing changes and documenting DoD. User stories are Data extraction, Dashboard, and Frontend | Zach, Howard, Imran
2022-03-09 | Stand up | Dashboard almost done. Data extraction has been slow due to other assignments | Zach, Howard
2022-03-16 | Stand up | Integrated data extraction with dashboard and finished sprint. Robbie was doing login but has gone MIA. Imran polished the navbar. Front end being pushed to next sprint. | Zach, Howard, Imran
2022-03-16 | Client Meeting | Was happy with initial data extraction. Discussed how to improve model. Client asked to focus on frontend for last sprint. | Zach, Howard, Imran
2022-03-16 | Sprint Review | Discussed that we should focus on cleaning up presentation and front end instead of backend and finishing. | Zach, Howard, Imran
2022-03-17 | Sprint Planning | Refined the backlog and added remaining user stories to sprint. Frontend, Multiple Selections and Export Data. | Zach, Howard, Imran
2022-03-23 | Stand up | Discussed our user stories. Multiple video selection done and export data done. Peer reviewed and suggested other funtionality. | Zach, Howard, Imran
2022-03-28 | Stand up | Discussed finalizing project and sprint. Finished Some front end styling. | Zach, Howard, Imran
2022-03-29 | Stand up | Front end completed, Set meeting for demo recording | Zach, Howard, Imran
2022-03-30 | Stand up/client meeting | Recorded Demo | Zach, Howard, Ikenna